## Sheet1
ID | Bug Title | Status
BUG-001 | A Vendor can still edit a tray while it is open in the Edit screen, even after the tray has been checked out. This should not be allowed. | Open
BUG-002 | Specialty Missing from Tray Details | Open
BUG-003 | Additional Info / Issue Description Field Does Not Support Multiple Lines | Open
BUG-004 | When an Admin removes a Manager and then refreshes the Hospital, a “Something went wrong” error appears first, followed by the user being logged out automatically. | Open
BUG-005 | Privacy Policy link on Terms and Conditions shows an error | Open
BUG-006 | Data is missing in terms and conditions | Open
BUG-007 | Label data field correction | Open
BUG-008 | Side menu icon changes when navigating to Overdue Revenue | Open
BUG-009 | Active tray list needs better status visibility | Open
BUG-010 | Error Message Shown on App When Deactivating Vendor from Admin | Open
BUG-011 | Error and Logout Occur After Removing Manager | Open
BUG-012 | Add Expiry Date to Tray Details | Open
BUG-013 | Backend ---- Incorrect Filters | Open
BUG-014 | Incorrect “Something went wrong” error shown on slow internet connection | Open
BUG-015 | Handle keyboard focus on check in and checkout | Open
BUG-016 | Payment popup is displayed before required validations on the Create Tray screen | Open
BUG-017 | Once account deletion is available on Staging, verify that all transactions and other related user data are handled correctly after the account is deleted. | Open
BUG-018 | On the Super Admin Dashboard, the amount displayed on the Total Revenue card is not fully visible. | Done
BUG-019 | The Manager Waived transaction type is not available in the transaction table or transaction filter. | Done
BUG-020 | The Settings section is not displayed in the Super Admin panel. | Done
BUG-021 | The price displayed in the list is being rounded off instead of showing the actual value. | Done
BUG-022 | The background color changes unexpectedly when the user regenerates or refreshes the screen. | Done
BUG-023 | When a tray is regenerated and the hospital is changed, the tray prices are not updated according to the selected hospital. | Done
BUG-024 | When a manager scans a QR code and then changes the hospital, the price remains at 0 instead of resetting based on the newly selected hospital. | Done
BUG-025 | An error message is displayed twice on the PIN Code screen | Done
BUG-026 | After scanning a QR code, navigating back automatically takes the user to the OTP screen. When the OTP is entered, the Manager Waive-Off amount is not displayed. | Done
BUG-027 | The Team Code expiry time is currently set to 15 minutes, but it should expire after 10 minutes. | Done
BUG-028 | A timer should be displayed for the verification code validity period. | Done
BUG-029 | A Resend option is required in the verification flow so users can request a new verification code. | Done
BUG-030 | After too many attempts, an incorrect message is displayed and the verification code is not received. | Done
BUG-031 | Create Tray – Expedite price changes when changing the date and returning to the original date. | Done
BUG-032 | checkout tray issue --- kiosk | Done
BUG-033 | Internet connection ---- kiosk | Done
BUG-034 | Phone number format issue - hospital managers | Done
BUG-035 | In Edit Hospital, when editing the number, the text cursor repeatedly moves to the end of the input field. | Done
BUG-036 | Changing the date and then creating a tray results in an incorrect expiry behavior. | Done
BUG-037 | On the My Trays screen, the loader continues running when the internet connection is turned off. | Done
BUG-038 | When the Case ID is removed while editing a tray, the updated information is not saved. | Done
BUG-039 | Back Navigation Should Not Work on QR Bottom Sheet | Done
BUG-040 | Incorrect Transaction Amount After Timezone Change | Done
BUG-041 | For a 5.50 overdue transaction, 5.00 is being deducted from my balance instead of the correct 5.50 amount. | Done
BUG-042 | When editing an existing Manager, the updated information is not being saved. | Done
BUG-043 | Staff Name Not Updated for Checkout Tray ---checkout by manager | Done
BUG-044 | Support Email link on Privacy Policy shows "Webpage not available" | Done
BUG-045 | Hospital Can Be Edited Even When No Manager Is Invited | Done
BUG-046 | When the Manager updates their profile information, such as their name, the updated information is not displayed after saving the changes. | Done
BUG-047 | The Manager Edit Profile screen does not currently provide a field to edit the manager's phone number. | Done
BUG-048 | The Manager Edit Profile screen does not display the manager's Email and Full Name. | Done
BUG-049 | A manager should not be allowed to be assigned to multiple hospitals using the same email address. | Done
BUG-050 | When a field has initial capitalization and additional letters are added while editing, the newly entered text does not follow the capitalization format. | Done
BUG-051 | The manager name should follow proper capitalization, e.g. John Smith instead of john smith --- hospital details | Done
BUG-052 | The email address displayed in the generated PDF is incorrect. | Done
BUG-053 | In the Expense Report, the Expired Tray count is incorrect. The count from Checkout is also being displayed along with the Expired Tray count. | Done
BUG-054 | Add pull down to refresh (checkout) | Done
BUG-055 | In Overdue Revenue, when the selected Custom Date filter is removed or cleared, the table does not reset. | Done
BUG-056 | The Start Date should begin from January 2026 --- overdue revenue custom date filter | Done
BUG-057 | The End Date should be limited to the current date --- overdue revenue custom date filter | Done
BUG-058 | The Tray ID should be removed from both Transactions and All Transactions screens in production. | Done
BUG-059 | In Edit Hospital, when editing the Hospital Name, the text cursor repeatedly moves to the end of the input field. | Done
BUG-060 | The PDF format is incorrect. | Done
BUG-061 | In the Custom Date section, the icons for Custom Date and Start Date are not properly aligned. | Done
BUG-062 | The search field placeholder in Overdue Revenue needs to be updated. | Done
BUG-063 | Remove terms and condition and privacy policy contact... hospital flow | Done
BUG-064 | Reduce height of Total Overdue Revenue section | Done
BUG-065 | The Vendor's First Name and Last Name should follow proper capitalization, e.g. John Smith instead of john smith. | Done
BUG-066 | Entire Transactions screen shifts when applying filters | Done
BUG-067 | In Tray listing, the Staff and Expired At text is not properly center-aligned | Done
BUG-068 | The Expired Tray count is not displayed as 0 when there are no expired trays. | Done
BUG-069 | In Generate Expense Report, when selecting a Custom Date, the selected date is not fully visible. | Done
BUG-070 | When there is no data available, the Generate Report action should not proceed. | Done
BUG-071 | Replace USD with the $ symbol. | Done
BUG-072 | Pull-to-refresh on the Expense Report displays two loaders instead of one. | Done
BUG-073 | In the Export Report section, the Hospital Name search field displays a character limit, which should not be shown. | Done
BUG-074 | User remains logged in after app reinstall | Done
BUG-075 | Expiry time format issue (extra :) | Done
BUG-076 | An incorrect username validation error is being displayed on the First Name field, requiring a minimum of 3 characters. | Done
BUG-077 | The Vendor's First Name and Last Name should follow proper capitalization, e.g. John Smith instead of john smith. | Done
BUG-078 | A "Type Null" error is displayed in the Transactions section. | Done
BUG-079 | Expiry time issue (95hrs 20 mins) - created tray | Done
BUG-080 | Not all trays are displayed on Checkout due to pagination issue | Done
BUG-081 | Incorrect Checkout Time displayed | Done
BUG-082 | Printout Queue feature | Done
BUG-083 | Android kiosk auto-scan + auto-print workflow | Done
BUG-084 | Email format issue | Done
BUG-085 | In the Vendor Edit Profile section, the Username field should be optional. | Done
BUG-086 | When a Hospital is deactivated after inviting a Manager, the invited Manager is unable to set a password. Repeated attempts to set the password do not complete successfully. | Done
BUG-087 | In the Vendor listing, the Status column is currently empty. | Done
BUG-088 | When a vendor is deactivated from the Admin Panel, the status appears to change successfully. However, after refreshing the page, the vendor becomes active again. | Done
BUG-089 | Resend Invite Email issue after deactivating | Done
BUG-090 | Active / Deactive issue | Done
BUG-091 | The invitation is successfully sent even though the entered email belongs to the same vendor account. | Done
BUG-092 | The vendor is unable to complete registration due to a username error. | Done
BUG-093 | Null is displayed in the login notification | Done
BUG-094 | After logging out and logging back in, navigating to Active Trays displays a "Null Strings" error. | Done
BUG-095 | Signup is not working – Username error is displayed | Done
BUG-096 | “No Info” Displayed for Staff After Hospital Checkout | Done
BUG-097 | When a Hospital user navigates to the Vendor module and opens a vendor's details, the system currently displays data from all hospitals. The Hospital user should only be able to view data associated with their own hospital. | Done
BUG-098 | Incorrect “Tray Is Not Expired” Message After Tray Creation | Done
BUG-099 | Incorrect "Tray is not expired" message is displayed after creating a tray | Done
BUG-100 | Apostrophe Missing in “Don’t Worry” Text on Signup Screen | Done
BUG-101 | Tray QR checkout removes total counts from All tabs | Done
BUG-102 | When a tray has been successfully checked out, an Expired notification is still displayed for that tray | Done
BUG-103 | After logging in as a Hospital user and opening the Scan QR screen, the system displays a "Staff already exists" message after some time, even though no QR code has been scanned. The user has only opened the camera. | Done
BUG-104 | Analytics Graph Count Does Not Update After Regenerated Tray Checkout | Done
BUG-105 | Incorrect Hospital API is being used on Vendor Edit Profile | Done
BUG-106 | When a Hospital user navigates to the Vendor module and opens a vendor's details, the All Hospital filter should not be available for Hospital users. | Done
BUG-107 | Edit Staff – Character limit not applied | Done
BUG-108 | When a user regenerates a tray while remaining on the Checkout screen, the tray is regenerated successfully, but the screen displays "No Tray Found." The updated tray data is only visible after manually refreshing the screen. | Done
BUG-109 | When the Manager’s full name is edited in Hospitals, the updated name is not reflected on the Hospital card immediately. The old name remains visible until the user logs out and logs in again. | Done
BUG-110 | Staff automatically add | Done
BUG-111 | When adding 50 characters to the Hospital Manager name, the values overflow outside the card instead of fitting within the card layout. | Done
BUG-112 | Limit Should Be Applied to Add Hospital and Invite Manager on admin | Done
BUG-113 | “Null” Displayed Instead of Hospital Manager Full Name | Done
BUG-114 | Admin reactivates a deactivated hospital, but the hospital details still show its status as Deactivated instead of Active. ---for raceaplit second | Done
BUG-115 | The First Name and Last Name of vendors are not being displayed in the Vendors section. | Done
BUG-116 | Invalid Format Error Appears When Enter Date field | Done
BUG-117 | “Null” is displayed when staff full name is not added | Done
BUG-118 | When the Manager’s full name is edited in Hospitals, the updated name is not reflected on the Hospital card immediately. The old name remains visible until the user logs out and logs in again. | Done
BUG-119 | Long Hospital Name Overflows Outside the Card | Done
BUG-120 | Data Too Long Error in Tray Additional Information | Done
BUG-121 | String Error When Adding Emojis in Tray Name | Done
BUG-122 | Status Column Should Be Removed from Hospitals | Done
BUG-123 | In transactions, search should be working with both hospital name and tray name as well in all over the project | Done
BUG-124 | Checkout Tray option should be visible only for Admin users (reporting details) | Done
BUG-125 | When navigating to Tray Details from the Recent Trays section on the Vendor Dashboard, no tray information is displayed. | Done
BUG-126 | Unable to add a Hospital – "Something went wrong" error is displayed | Done
BUG-127 | Hospitals with an active manager should not appear in the Hospital dropdown | Done
BUG-128 | Expired tray billing logic needs to be finalized | Done
BUG-129 | Expiration timing logic is not fully correct yet | Done
BUG-130 | Daily post-expiration notifications | Done
BUG-131 | Checkout authorization must use a separate user badge QR code | Done
BUG-132 | Email / SMTP configuration for SteriPass | Done
BUG-133 | The Tray Total Cost is displayed with incorrect decimal formatting. For example, values such as 2.50 and 5.50 are incorrectly shown as 2.5.00 and 5.5.00. | Done
BUG-134 | Saving button is cut off on the Settings screen | Done
BUG-135 | On the All Hospitals module, the All Transactions option on the Hospital Details screen is not clickable. Users are unable to navigate to the transactions list. | Done
BUG-136 | In the All Vendors → All Trays screen, the Expiry Time is displayed incorrectly. The application currently shows 120 hours, whereas the correct expiry time should be 95 hours. | Done
BUG-137 | In All Vendors → View Details → All Transactions, the Type filter contains an option for Expedite, but its spelling is incorrect. | Done
BUG-138 | Unable to check out tray due to Staff ID error | Done
BUG-139 | Replace "Managed By" with "Manager Name" on the Manager Details screen | Done
BUG-140 | Replace "Staff Email" with "Manager Email" on the Manager Details screen | Done
BUG-141 | Newly added manager is displayed as "Active" instead of "Invite Sent" | Done
BUG-142 | Show only Associated Hospital filter in the All Trays section of Vendor Details | Done
BUG-143 | Filters are not reset when switching tabs | Done
BUG-144 | Mobile responsive | Done
BUG-145 | Mobile responsive ---- The status bar color is white until the navigation menu is opened. | Done
BUG-146 | Mobile responsive ---- The bottom section where links are added remains white until accessed via the navigation menu. | Done
BUG-147 | When attempting to log in, the app shows a “User not found” error, but the loader remains visible. | Done
BUG-148 | When entering an incorrect password on the login screen, the loader keeps spinning. | Done
BUG-149 | Back button not working on Update Password screen | Done
BUG-150 | When navigating to the Signup or Login screen, search results from the previous user session appear. | Done
BUG-151 | When clicking Proceed, the physician name and tray name fields get cleared. | Done
BUG-152 | The color that should change based on expiration time is not updating correctly. | Done
BUG-153 | Null check operator error when going to View Account or Checkout without searching any account | Done
BUG-154 | The app does not have a logo. | Done
BUG-155 | The spelling of “photos” is wrong in (take photos of each slide). | Done
BUG-156 | It’s not showing an expiry time of more than 23 hours. | Done
BUG-157 | Multiple images are being selected from the gallery, but only the first one is being added. | Done
BUG-158 | When I drag the bottom sheet to close, the tray gets added but the “Create Tray” screen does not close. | Done
BUG-159 | Google account is logging in even when you enter any random password. | Done
BUG-160 | Hospital is not changing when we try to update it. | Done
BUG-161 | The Checked out trays will not appear in the Active tray. | Done
BUG-162 | The image is not being removed. | Done
BUG-163 | A null check operator error appears, but checkout still completes when no hospital is selected. | Done
BUG-164 | I used a photo of a single QR code and applied the same QR code for checkout in all trays, and the checkout is still being completed successfully. | Done
BUG-165 | The token has expired, but the user is not logged out. | Done
BUG-166 | The spelling of Steri-Pass is incorrect. | Done
BUG-167 | Favicon is missing. | Done
BUG-168 | Left and right margins are missing on the entire landing page. | Done
BUG-169 | The font of “Smart Tracking Led by Vendors and Sales Reps” is bold. | Done
BUG-170 | The font of “About Steri-Pass” is bold. | Done
BUG-171 | The font of “From Confusion to Clarity, Steri-Pass Solves It All” is bold. | Done
BUG-172 | The font of “Frequently Asked Questions” is bold. | Done
BUG-173 | Solution link is missing. (header, footer) | Done
BUG-174 | Navigation on the login page is incorrect. | Done
BUG-175 | All boxes should have the same height. | Done
BUG-176 | Mobile responsive ---- In Smart Tracking, the heading and paragraph appear at the top and the image appears below. | Done
BUG-177 | Footer ---- The “Total Control” line should appear together on the first line. | Done
BUG-178 | Mobile responsive ---- Copyright should appear at the very end of the page. | Done
BUG-179 | Mobile responsive ---- Clicking Login redirects to Alpha Arc on the App Store. | Done
BUG-180 | Link is missing (Get started) | Done
BUG-181 | Incorrect FAQs have been added. | Done
BUG-182 | On refresh, the navigation behaves incorrectly. | Done
BUG-183 | When I change the hospital name in Regenerate Tray, it doesn’t update properly. | Done
BUG-184 | I edited the tray and the hospital name is changed, but the tray still appears in the previous hospital’s list until I go back and then return again. | Done
BUG-185 | After purchasing the expired tray, the total cost is showing $3, whereas it should be $5, because the cost of the expired tray is $5. | Done
BUG-186 | Image is stretched, not displayed with correct pixels | Done
BUG-187 | Buttons without links should be disabled on Landing Page | Done
BUG-188 | Automated warning notifications before expiration | Done
BUG-189 | Expired tray notifications | Done
BUG-190 | Rename label action | Done
BUG-191 | “Generate New Label” workflow is incorrect | Done
BUG-192 | One-time-use QR code system | Done
BUG-193 | Incorrect URL redirection (next link not loading properly) | Done
BUG-194 | Username field missing validation | Done
BUG-195 | Vendor Name Missing | Done
BUG-196 | Search Functionality Not Working | Done
BUG-197 | Incorrect Expiry Status on Checkout | Done
BUG-198 | Unnecessary Columns in Hospital Vendor Screen | Done
BUG-199 | Responsive issue | Done
BUG-200 | Forgot Password functionality not working | Done
BUG-201 | Multiple toast messages appearing for a single action | Done
BUG-202 | “Select Hospital” text color does not match design | Done
BUG-203 | App logo does not match design | Done
BUG-204 | Incorrect capitalization for “Platform Administration” | Done
BUG-205 | Incorrect capitalization for “Hospital Workspace” | Done
BUG-206 | Hospital screen UI does not match design | Done
BUG-207 | Phone number format does not match design | Done
BUG-208 | Proper placeholder text missing/inconsistent in input fields | Done
BUG-209 | Newly created hospital not appearing in dropdown | Done
BUG-210 | “Search Hospital” field missing in Invite Manager modal | Done
BUG-211 | Button should be disabled initially | Done
BUG-212 | Previously selected text persists when modal is reopened | Done
BUG-213 | Removed manager should be automatically logged out | Done
BUG-214 | Newly added user shows “Active” status incorrectly | Done
BUG-215 | Text pre-selected when editing hospital | Done
BUG-216 | Incorrect text displayed when search returns no results | Done
BUG-217 | Reporting screen UI does not match design | Done
BUG-218 | Detail screen not opening in any module | Done
BUG-219 | Cross (✕) icon appears incorrectly next to hospital dropdown after selection | Done
BUG-220 | Analytics screen UI does not match design | Done
BUG-221 | Dashboard displays incorrect data | Done
BUG-222 | Dashboard screen UI does not match design | Done
BUG-223 | Icons on detail screen do not match design | Done
BUG-224 | Additional information not displaying | Done
BUG-225 | Image size does not match design | Done
BUG-226 | Weight unit not displayed | Done
BUG-227 | Decimal values not displayed in Total Cost | Done
BUG-228 | Updated data from mobile not reflecting on web listing until detail view is opened | Done
BUG-229 | Expiry of purchase not updating on refresh | Done
BUG-230 | Edit Profile functionality not working | Done
BUG-231 | Values not resetting on Change Password screen | Done
BUG-232 | Duplicate eye icons displayed on Change Password screen | Done
BUG-233 | Fav icon is missing | Done
BUG-234 | Vendor dashboard UI does not match design | Done
BUG-235 | Change Password screen UI does not match design | Done
BUG-236 | Profile modal UI does not match design | Done
BUG-237 | Missing Phone Number Validation | Done
BUG-238 | Long Text Not displayed with dots | Done
BUG-239 | Edited Hospital Not Updating in Dropdown | Done
BUG-240 | Vendor Data Disappears on Deactivate/Reactivate | Done
BUG-241 | User Logged Out on Invalid Credentials in Change Password | Done
BUG-242 | Incorrect Redirection on Super Admin Logout | Done
BUG-243 | Incorrect Message on User Forgot Password | Done
BUG-244 | Resend OTP Not Working (Admin) | Done
BUG-245 | OTP Field Should Restrict Input to 6 Digits | Done
BUG-246 | Back Navigation Allowed After Logout | Done
BUG-247 | “Sales Associate” role not visible in Role list | Done
BUG-248 | Long text not wrapping causing button to be hidden | Done
BUG-249 | “Something went wrong” message appears on automatic logout | Done
BUG-250 | Icons not visible on Change Password and Logout options (Admin) | Done
BUG-251 | Check-in and Check-out arrows missing in Vendors section | Done
BUG-252 | Menu names not visible in side navigation (Hospital flow) | Done
BUG-253 | Change Password not working via Forgot Password flow | Done
BUG-254 | Autofill issue: Password auto-filled and email appears in unrelated fields | Done
BUG-255 | Mobile responsive | Done
BUG-256 | Text should be displayed in a single line | Done
BUG-257 | Pie chart scales incorrectly on browser zoom (90%) | Done
BUG-258 | “Remember your password?” text should be removed when navigating from Change Password to Forgot Password | Done
BUG-259 | Favicon needs to be updated | Done
BUG-260 | Reporting tray not visible in Evergreen Medical Center hospital | Done
BUG-261 | Reporting detail screen UI does not match design | Done
BUG-262 | Copied text not pasting on code screen | Done
BUG-263 | Enter key should work after entering code | Done
BUG-264 | Tray count increases incorrectly on clicking "View All" | Done
BUG-265 | Image Preview Not Closing | Done
BUG-266 | Incorrect Navigation on Hospital Change | Done
BUG-267 | Search not working in Reporting and Vendors modules (global data shown instead) | Done
BUG-268 | Incorrect data displayed when filters are applied | Done
BUG-269 | Incorrect data displayed in Analysis pie chart | Done
BUG-270 | Incorrect $3 deduction on Re-generate Tray | Done
BUG-271 | No message shown when tray is not expired | Done
BUG-272 | Archived tray cannot be edited | Done
BUG-273 | Tray status not updating after checkout, purchase expiry until navigation | Done
BUG-274 | Expired trays appearing in Checkout after tab switch | Done
BUG-275 | User is able to proceed without accepting Terms and Conditions | Done
BUG-276 | Tray checkout not working (error displayed) | Done
BUG-277 | Checked-out tray removed from "All" tab | Done
BUG-278 | Updated staff data not reflected in QR scan until refresh | Done
BUG-279 | Forgot password not working from Change Password | Done
BUG-280 | Delete option should be hidden when only one card exists | Done
BUG-281 | Incorrect spelling of Current Password (Change Password) | Done
BUG-282 | User remains logged in after reinstalling the application and "Unauthorized" error is displayed during logout | Done
BUG-283 | Unable to add card due to error | Done
BUG-284 | Validate Regenerate tabs routing | Done
BUG-285 | Improve the loading time of Regenerate Tray | Done
BUG-286 | Pull down to refresh (My Trays) | Done
BUG-287 | Non-editable fields should be displayed in a disabled state in Edit Tray | Done
BUG-288 | Routing issue in whole web (Hospital, Vendor, Admin flow) | Done
BUG-289 | Incorrect vendor name is displayed in Transactions | Done
BUG-290 | App closes instead of navigating back from Scanner screen using Android navigation | Done
BUG-291 | Unable to create a new account | Done
BUG-292 | Unable to add a new card | Done
BUG-293 | No message is displayed when camera permission is denied | Done
BUG-294 | Incorrect amount is deducted during transaction | Done
BUG-295 | Loader remains visible after closing the Gallery selection sheet (Edit Tray) | Done
BUG-296 | App navigates back to My Trays after cancelling the Camera permission popup | Done
BUG-297 | Incorrect navigation after changing route from Admin to Hospital on Forgot Password screen | Done
BUG-298 | Terms & Conditions and Privacy Policy issues | Done
BUG-299 | Display an empty state for the Pie Chart when no data is available | Done
BUG-300 | Add an Expedite column to the Vendor Dashboard | Done
BUG-301 | Regenerated tray is not displayed on the Checkout screen until the page is refreshed | Done
BUG-302 | Original tray is removed after regenerating a tray | Done
BUG-303 | Incorrect count is displayed in the Trays Remaining column | Done
BUG-304 | Infinite loader is displayed on the My Trays screen after recreating an account with the same email | Done
BUG-305 | Spelling of waive is incorrect -- tray details | Done
BUG-306 | Update Text Message for Email and SMS (Manager pin scrren) | Done
BUG-307 | Update Success Message for Email and SMS (resend pin) | Done
BUG-308 | In the Overdue Revenue section, the Download button should not be available when there are no transactions. | Done
BUG-309 | Multiple time we click on “Sign In,” the account gets logged in. | Done
BUG-310 | The Checkout By Manager information is not displayed when a tray is checked out by a manager. | Done
BUG-311 | The image area in the Issue View does not have a fixed position, causing the description to shift while the image is loading. | Done
BUG-312 | The Checkout By Manager information is not displayed when a tray is checked out by a manager. | Done
BUG-313 | The Description text is currently displayed in bold formatting. | Done
BUG-314 | Label printing configuration still needs fixing | Done
BUG-315 | Update Manager Waive Text in Tray Details | Done
BUG-316 | Tray Details Screen Does Not Return to Top | Done
BUG-317 | Incorrect Expired Status Shown for Checkout Trays (vendor dashboard) | Done
BUG-318 | Incorrect No-Reply Email Address Displayed in PDF | Done
BUG-319 | Remaining Count Does Not Update After Tray Checkout (back navigation and refresh) | Done
BUG-320 | Case ID Is Still Displayed When Regenerating a Tray After Being Disabled by Admin | Done
BUG-321 | The Pull-to-Refresh functionality is missing from the Edit Tray screen. | Done
BUG-322 | Calendar Is Not Displayed Properly in Date Filter on Mobile Responsive | Done
BUG-323 | On mobile responsive, when the user opens the Edit Hospital modal from Hospital Details, the Edit Hospital button remains visible. | Done
BUG-324 | When a hospital with a short name is selected, longer hospital names are cut off in the dropdown list. | Done